# Harbour Library Renovation

Project update for the board · October 2026

# Summary

The reading room reopened on 6 October, two weeks ahead of the plan. Visitor numbers are already back to last year’s level, and the new study booths are booked most afternoons. The children’s floor is the last stage, with work starting in November.

# What changed

New lighting and acoustic panels in the reading room

Twelve bookable study booths with power at every desk

A step-free entrance from Quay Street

# Budget

Spending is on track. The contingency covers the extra structural work found under the old stage.

| Stage | Budget | Spent |
| --- | --- | --- |
| Reading room | $420,000 | $408,500 |
| Study booths | $96,000 | $91,200 |
| Children’s floor | $310,000 | $12,000 |

# Next steps

The children’s floor closes on 3 November. Story time moves to the reading room’s east corner until the spring, and the holiday programme runs as usual.

We will bring the final furniture order to the December meeting for approval, along with a revised opening date.